## Project Info

Client: Frondoor

Project: Frontdoor-PL/SQL Service-Based Modernization

Date: August, 6th, 2026

## Meeting Objectives

An effective and well-executed internal project kickoff will help the project team with the following:

- Be aware of any key insights that 66 learned via the pre-sales process (such as why the client chose 66degrees for the project, budget/pricing strategies, client personalities/politics, cautionary guidance, special callouts, etc.)

- Understand the project scope and deliverables; and equally important, the Solution Assumptions/Out of Scope/Client Responsibilities boundaries/parameters that were used during pre-sales to shape and estimate the project

- Understand the client’s objectives, success criteria, and/or how the client will derive value from the project

- Clarity and mutual expectations with respect to workstream and Deliverables ownership

- Identify any Risks that need to be managed from the outset of the project

- Establish an action plan to further set the project into motion

- Align on external kickoff agenda, content, and responsibilities

## Agenda

Use the following agenda as guidance for the internal project kickoff.

Note: The expectation should be that project team members have reviewed the contract (e.g. SOW, Work Order, Change Order, etc) prior to the internal kickoff meeting.

| Agenda | Link | Definition |
| --- | --- | --- |
| Team Introductions | Project Team and Roles | Team meet & greet: - Name/Team/Title - Location/Time Zone - Have you worked on similar projects and/or this client in the past? - Little-known or fun fact ice-breaker |
| Client Objectives & Value | Objectives | Team discussion about the client’s desired outcomes, what will provide them the greatest value from the project – and why. |
| Migration Approach | Implementation Approach | Team discussion, clarification, establish a common understanding, focused on: - Project Approach - Project Timeline |
| Project scope | Project Scope | Team discussion, clarification, establish a common understanding, focused on: - Project Scope - Project Approach & Activities |
| Deliverables Ownership | Deliverables Ownership | Review the table below. |
| Sales-to-Delivery Handoff Review | Link to S2D Doc | Debrief on key take-aways, open items, issues, etc. from the S2D Handoff. Keep it quick and to-the-point! |
| Questions, Risks & Issues | Risk Management | Capture any open questions, risks, issues. |
| Action Items | Action Items | Discuss and complete the table below. |

## Project Team & Roles

| Name | Project Role(s) | Assignment Start Date | Project Allocation | Attended Internal Kickoff? |
| --- | --- | --- | --- | --- |
| Amit Athalye | Delivery Manager | 7/27/2026 | 45 | Yes |
| Farheen Fathima | QA Engineer | 7/27/2026 | 45 | TBD |
| Jay Zende | Cloud Engineer | 7/27/2026 | 45 | Yes |
| Kavitha A N | Cloud Engineer | 7/27/2026 | 45 | TBD |
| Nicholas Brandon | Cloud Architect | 7/27/2026 | 20 | TBD |
| Paulo Masis | App Dev Architect | 7/27/2026 | 20 | Yes |
| Pradeep Belgavkar | Back End Engineer | 7/27/2026 | 45 | Yes |
| Rajeshwari Betageri | QA Lead | 7/27/2026 | 45 | Yes |
| Rohan Gundi | Back End Engineer | 8/2/2026 | 45 | TBD |
| Sneha H | QA Engineer | 7/27/2026 | 45 | TBD |
| Surya Manduri | App Dev Architect | 8/2/2026 | 45 | Yes |
| Alexandre Little | App Dev Architect | 7/27/2026 | 20 | Yes |
| Arunakumara YB | App Dev Architect | 8/2/2026 | 45 | Yes |
| Jackie Scherer | Delivery Manager | 8/2/2026 | 40 | Yes |
|  |  |  |  | Yes |
|  |  |  |  | Yes |

Note to Project Team Members: Please familiarize yourself with the key accountabilities of your project role(s).

Note to Project Manager: Are all 66Way key roles aligned to project team members? Are there gaps in key roles? If so, log this as a Risk and engage your Portfolio Lead as needed.

## Client Objectives & Value

### Primary Objectives

- Modernize legacy Oracle PL/SQL packages by translating them into independent .NET REST microservices.

- Decouple business logic from the Oracle database.

- Build containerized microservices deployed on AWS EKS using Docker.

- Enable cloud-native architecture while preserving existing business functionality.

- Improve system resiliency through a modern microservices architecture.

- Support incremental migration using the Strangler Fig deployment pattern.

## Business Value:

- Multi-region cloud resiliency

- Reduce dependency on Oracle database business logic

- Improvement in Improve scalability and maintainability

## Implementation Approach

| ## Stage | ## Purpose |
| --- | --- |
| ## Prepare | ## Team mobilization, governance, tooling check (Phase 1 only) |
| ## Define | ## AI-assisted PL/SQL specification mining, service contract scoping, requirements validation with Frontdoor BA/SMEs |
| ## Design | ## Sequence diagrams, OpenAPI specs, DTO-to-Oracle-schema mappings, K8s manifest patterns, service mesh routing design |
| ## Plan | ## Sprint plan, release plan, test strategy, UAT scheduling with Frontdoor |
| ## Value Checkpoint | ## Sponsor sign-off gate before Build commitment |
| ## Build | ## Sprint-based AI-assisted translation, unit/integration/contract tests, code review, mesh routing config |
| ## Verify | ## QA execution (functional, integration, contract, performance parity), UAT coordination |
| ## Operate | ## SRE handover, runbooks, dashboards, knowledge transfer, phase close-out (no hypercare) |

| 66Way stage | Phase 1 (wks) | Phase 2 (wks) | Phase 3 (wks) | Notes |
| --- | --- | --- | --- | --- |
| Prepare | 1 | — | — | Only Phase 1; team continuous from P0 |
| Define | 2 | 1 | 1 | Architect + Sr Eng-led requirements (PL/SQL spec extraction with AI) |
| Design | 2.5 | 1 | 2 | Sequence diagrams, OpenAPI, IaC patterns per service (P3 includes Card Security PCI extension design — 2 wks wall-clock) |
| Plan | 1 | 1 | 1 | Sprint plan, test strategy, value checkpoint prep |
| Value Checkpoint | <1 | <1 | <1 | Sponsor sign-off prior to Build |
| Build | 9 | 8 | 7 | Dual Pod A/B sustained HITL; §3 build-hour inventory unchanged; wall-clock shortened via overlap and parallel capacity (see §2.5) |
| Verify | 3 | 2 | 2 | QA + UAT support (Frontdoor-led UAT); QA/DM hours in §10 fund parallel lanes, not shorter calendar gates |
| Operate | 2 | 1 | 1 | SRE handover + KT + close-out only (no hypercare) |
| Total active | ~21 | ~14.5 | ~14.5 | P2 starts P1 week 6; P3 starts P2 week 4 — phase overlap + dual Build pods → ~6.0 mo program wall-clock |

## Phase 0 — Program Initiation & Foundation

## Phase 0 establishes the platform substrate, AI tooling, shared libraries, Istio strangler-routing templates (against Frontdoor's existing mesh), and CI/CD pipelines before Phase 1 Build begins. All deliverables are consumed by downstream phases.

## 1.1 Governance & Mobilization

## Draft and ratify the program charter, RACI matrix, communication plan, and steering-committee cadence.

## Establish IST (India Standard Time) follow-the-sun delivery management coverage.

## Conduct stakeholder kickoff workshops; publish the program communications plan.

## 1.2 Reference Architecture & Standards

## Author the reference architecture document: .NET 8 on existing EKS, Oracle connectivity via Oracle.ManagedDataAccess / ODP.NET, AWS KMS for cryptographic key management, service-mesh-mediated deployment with strangler fig traffic routing.

## Define REST/OpenAPI 3.1 API standards: error model, pagination, versioning conventions, external-caller authentication via Amazon Cognito / API Gateway.

## Create the sequence-diagram template and doc-as-code toolchain (Mermaid + ADRs); scope limited to caller-to-service flows.

## Build the .NET solution template: project structure, Polly for downstream HTTP resilience, Serilog structured logging, OpenTelemetry instrumentation, AutoMapper, MediatR in-process mediator.

## 1.3 Cloud Platform Setup

## Configure K8s namespaces, RBAC policies, and AWS Secrets Manager integration on the existing EKS cluster.

## Author K8s manifest templates: Deployment, Service, Ingress, ConfigMap, Secrets, HPA, with Kustomize overlays for environment promotion (dev → staging → production).

## Build CI/CD pipelines: AWS CodeBuild + GitHub Actions for build → test → scan → kubectl apply promotion.

## Configure observability baseline: Amazon CloudWatch dashboards, AWS X-Ray distributed tracing, SLO definitions.

## 1.4 Security Foundation

## Conduct PCI scope analysis for the Card Security and Crypto Primitives shared libraries; produce AWS KMS / AWS CloudHSM integration design.

## Define the identity model: external-caller authentication (Amazon Cognito / API Gateway), per-service IAM roles for AWS resource access.

## 1.5 AI Enablement

## Configure Cursor IDE and LLM agent infrastructure; author per-domain prompt templates and translation rules.

## Build the PL/SQL parser and spec-extractor agent: call-graph extraction, side-effect tagging, parameter-contract identification.

## Produce the translation cookbook with golden examples: translate one small PL/SQL package (CONTEXT_API, 27 LOC) end-to-end through the full pipeline — AI translation, human review, test generation, K8s deploy, mesh routing — to calibrate throughput rates and validate the dead-code assumption before Phase 1 commitment.

## 1.6 Shared Library Construction

## Six shared libraries are built, tested, packaged as NuGet, and published before Phase 1 Build. Each is consumed in-process (no network calls) by the 18 microservices.

| ## Library | ## Source PL/SQL packages | ## Effective LOC | ## Technical scope |
| --- | --- | --- | --- |
| ## Core Utilities | ## COMMON_FUNC, COMMON_FUNC_SQL, PKG_COMMON, P_LIBRARIES, STRINGOBJ, ASSERT, VALIDATION_FUNCTIONS, ETL_COMMON, CONTEXT_API | ## 13,780 | ## String manipulation, date/time formatting, data validation, assertion framework, ETL helpers, context-passing utilities. ~70% of this code translates near-automatically with AI; human effort focuses on edge-case parity (Oracle-specific date arithmetic, NLS collation, TO_CHAR format masks). |
| ## Error Handling | ## COMMON_FUNC_ERROR_HANDLER | ## 314 | ## Structured exception capture, Serilog integration, correlation-ID propagation. Replaces Oracle RAISE_APPLICATION_ERROR and custom exception-table logging with idiomatic .NET IExceptionHandler middleware. |
| ## Feature Flags & Config | ## SSI_FEATURES + FLAG_CS1 | ## 59 | ## Database-driven feature toggle lookup against ssi_feature_toggle table. FLAG_CS1 implemented from src/additional_code/functions/flag_cs1.sql (ETL coverage-flag helper). |
| ## File & S3 Storage | ## FILEOP + adapters for prod.star_cloud / clob_to_file | ## 1,019 | ## Replaces Oracle UTL_FILE and object-storage calls with an AWS S3-backed IStorageService. clob_to_file source is in src/additional_code/procedures/clob_to_file.sql. prod.star_cloud still has no local implementation (adapter from call sites). |
| ## Crypto Primitives | ## STARCRYPTO | ## 349 | ## Replaces the insecure custom STARCRYPTO encryption with AWS KMS-backed key management. Provides IEncryptionService with AES-256-GCM envelope encryption. PCI premium reflects mandatory FIPS validation, security-architect review, and compliance documentation. |
| ## AHS Queue Persistence | ## AHS_QUEUE_FUNCTIONS | ## 334 | ## CRUD layer over AHS_QUEUE / AHS_QUEUE_DETAILS tables via Oracle EF Core. Consumed in-process (NuGet) by Cancellation, Sales Transaction, Work Order & Fulfillment, and Customer services. This is a database-table abstraction, not inter-process messaging; the inter-service queue wrappers (ENQUEUE_MESSAGE, DEQUEUE_MESSAGE, PROC_INCREMENT_USAGE_COUNT) remain out of scope. |

## 1.7 Istio Routing Configuration (Existing Mesh)

## Frontdoor operates Istio on the target EKS cluster. Phase 0 does not install or reconfigure the mesh control plane. Scope is limited to project-specific traffic routing and security policies for the 18 microservices:

## Design strangler fig routing strategy aligned with Frontdoor's Istio conventions: VirtualService / DestinationRule patterns, traffic-splitting weights, canary rollout templates, rollback procedures.

## Validate integration with the existing Istio deployment: confirm sidecar injection and namespace/gateway patterns for program workloads; document mesh ingress and operational handoffs from Frontdoor platform teams.

## Author project-scoped VirtualService and DestinationRule templates for strangler fig cutover (legacy Oracle REST ↔ new .NET); define per-service K8s service accounts and project-scoped AuthorizationPolicy (and PeerAuthentication overrides only where the existing baseline requires them).

## Execute the strangler fig routing proof-of-concept: dual-route one pilot service between legacy Oracle REST and new .NET, validating weighted traffic splitting, canary rollout, rollback procedure, and latency overhead benchmarking on the live mesh.

## 1.8 QA Foundation

## Define the QA strategy: contract tests (consumer-driven), mutation tests, behavioral-parity test model (PL/SQL output vs .NET output for identical inputs), performance baselines.

## Phase 1 — Translate & Decommission First 45 PL/SQL Objects

## Phase 1 is the largest and most foundational phase. It establishes patterns, validates assumptions, and delivers the first 13 services to production traffic.

## Services delivered (13): Customer · Contract · Pricing & Revenue · Dispatch · Work Order & Fulfillment (subset) · Invoicing · Payment · Vendor (subset) · Vendor Invoice & Writeoff · Commission & Territory · Finance Integration · Card Security · Reporting (subset) · Service Order (subset).

## 2.1 Prepare

## Finalize the Phase 1 plan, RAID log, and governance cadence.

## Onboard engineering leads (onshore and offshore); validate tooling access and development environment.

## Confirm 13-service scope and dependency map (PL/SQL packages → target services).

## Brief sponsor; QA Lead reads in on test strategy.

## 2.2 Define — Discovery & Requirements

## Without a dedicated BA, requirements extraction is led by App Dev Architects and Senior Engineers using AI-assisted PL/SQL specification mining:

## Per-service contract scoping (13 services). For each service, identify the public API surface by analyzing PL/SQL package specifications: exported procedure/function signatures, parameter types, return types, exception contracts.

## PL/SQL deep-dive (45 packages). For each package body, perform AI-assisted call-graph analysis to identify: live vs. dead code paths, side effects (DML, commits, external calls), cross-package dependencies, Oracle-proprietary constructs requiring special handling (UTL_FILE, DBMS_AQ, PRAGMA AUTONOMOUS_TRANSACTION, HTP/HTF web toolkit calls).

## Cross-service dependency validation. Map the 11 critical and 17 strong inter-service couplings that touch Phase 1 services; identify data contracts at each boundary.

## Supplemental source. Phase 1 standalone procedures are in src/additional_code/ (CREATE_AP_JDE_FILE, CREATE_GL_JDE_FILE, CREATE_VENDOR_JDE_FILE, PPUB_INVOICE_DIST, PROC_MISC_CASH_STAGING, PROC_OAP_PAYMENTS_STAGING, PROC_CREDIT_MEMO_APPLY). Map to Finance Integration and Vendor Invoice & Writeoff services. PROC_CREDIT_MEMO_APPLY orchestrates P_LIBRARIES.fpub_credit_memo_apply (also in scoped packages).

## Frontdoor-BA liaison. Weekly validation gates with Frontdoor's BA pool to confirm extracted requirements.

## 2.3 Design — Solution Design

## API design and OpenAPI synthesis. For each of the 13 services, produce an OpenAPI 3.1 specification using AI-generated drafts with human review. Specifications define resource models, endpoint paths, HTTP methods, request/response schemas, error responses, and pagination.

## Sequence diagrams. AI-drafted caller → service → database interaction diagrams for each major endpoint, reviewed and refined by architects.

## DTO-to-Oracle-schema mapping. For each service, map C# DTOs and entity classes to existing Oracle tables, views, and column types. Define Oracle EF Core entity configurations or Dapper query contracts. No schema changes — mapping is read/write against existing structures.

## K8s manifest pattern. Per-service Deployment, Service, Ingress, ConfigMap, HPA configurations derived from Phase 0 templates.

## Card Security threat model. PCI DSS-aligned threat model for the Card Security service; AWS KMS integration design for card-number encryption/decryption replacing STARCRYPTO.

## Test strategy per service. Define test-data sets, parity-test scenarios (PL/SQL output vs .NET output), integration-test boundaries.

## 2.4 Plan

## Sprint plan: decompose 13 services into sprint-sized work packages across the Build stage.

## Release plan: service deployment sequence respecting inter-service dependency order (e.g., Customer Service before Contract Service; Contract Service before Dispatch Service).

## UAT scheduling: book test slots and environment access with Frontdoor.

## 2.5 Value Checkpoint

## Sponsor walkthrough: present Define/Design outcomes, confirmed scope, risk register, and Build plan.

## Dead-code re-baseline gate. If the Phase 0 golden-example exercise and Phase 1 Define call-graph analysis reveal the live-code ratio deviates significantly from 50%, scope is recalibrated before Build commitment.

## 2.6 Build — Translation, Test, Integration, Deploy

## The Build stage translates 45 PL/SQL objects into 13 services in 2-week sprints. Per-service work follows a repeatable pipeline:

## Per-service translation pipeline:

## AI-assisted code translation. For each PL/SQL procedure/function in the package body, generate a C# implementation using the calibrated LLM agent. Oracle-specific constructs are handled as follows:

| ## PL/SQL construct | ## .NET equivalent |
| --- | --- |
| ## UTL_FILE read/write | ## IStorageService (File & S3 Storage lib) |
| ## UTL_SMTP email | ## INotificationService (Notification Service REST call) |
| ## DBMS_CRYPTO / STARCRYPTO | ## IEncryptionService (Crypto Primitives lib, AWS KMS) |
| ## prod.star_cloud.* | ## IStorageService.GetObject/PutObject/ListFiles/DeleteFile (no local source; call-site adapter) |
| ## prod.clob_to_file / clob_to_file | ## IStorageService.WriteClobToFile (from additional_code/procedures/clob_to_file.sql) |
| ## prod.cost_center2department / cost_center2department | ## Adapter in Finance Integration Service (from additional_code/functions/cost_center2department.sql) |
| ## PRAGMA AUTONOMOUS_TRANSACTION | ## Separate DbContext with independent SaveChanges |
| ## HTP/HTF web toolkit | ## Eliminated — REST responses replace HTML generation |
| ## DBMS_AQ enqueue/dequeue | ## Out of scope (Frontdoor-owned) |
| ## Oracle %ROWTYPE / %TYPE | ## Strongly-typed C# DTOs |
| ## Oracle REF CURSOR | ## IAsyncEnumerable<T> or materialized List<T> |
| ## Oracle exceptions (RAISE_APPLICATION_ERROR) | ## Domain exception classes → ProblemDetails HTTP responses |
| ## Autonomous transactions (logging/locking) | ## Scoped DbContext with independent unit of work |

## Unit test generation. AI-generated unit tests covering: input validation, happy-path business logic, edge cases identified during Define, exception paths. Target: ≥80% branch coverage per service.

## Integration test generation. Tests that exercise the full HTTP → Controller → MediatR Handler → Repository → Oracle roundtrip. Parity tests compare .NET output against PL/SQL output for identical input sets.

## Contract test authoring. Consumer-driven contract tests for inter-service API boundaries (Pact or equivalent).

## Code review. Mandatory pair-review by senior engineer for all AI-generated code. Financial logic (commission calculation, write-off, credit-memo application, deferred revenue) receives additional review for semantic drift.

## Containerization. Multi-stage Dockerfile per service: build → test → publish → runtime image. Base image: mcr.microsoft.com/dotnet/aspnet:8.0.

## K8s manifest generation. Per-service Deployment, Service, Ingress, ConfigMap, Secrets (Oracle connection strings via AWS Secrets Manager), HPA. Kustomize overlays for dev/staging/production.

## Istio routing configuration. Per-service VirtualService and DestinationRule (and project-scoped AuthorizationPolicy where required) defining: initial traffic split (100% legacy / 0% .NET), canary rollout template, weighted-split progression rules, and rollback trigger conditions — applied to Frontdoor's existing Istio mesh; no control-plane installation.

## Phase 1 service-specific scope:

| ## Service | ## PL/SQL packages translated | ## Key technical concerns |
| --- | --- | --- |
| ## Customer Service | ## CUSTOMER_BO, CUSTOMER_FUNCTIONS, PROPERTY_FUNCTIONS / F_GET_FORMATTED_ADDRESS, PHYSICALADDRESS, PHYSICALADDRESS_DA | ## Bidirectional coupling with Contract and Web Portal services; address formatting and geocoding logic |
| ## Contract Service | ## CONTRACT_BO, CONTRACT_DA, CONTRACT_FUNCTIONS, CONTRACT_COVERAGE, MAINTAIN_CONTRACT | ## Highest fan-in service (11 dependents); contract eligibility, coverage verification, terms management |
| ## Pricing & Revenue | ## COMPUTE_DIST_PAYABLE, PKG_DEF_REVENUE_LIBS, PRICE_CONTRACT_WARRANTY (partial) | ## Commission calculation, deferred-revenue accounting — financial logic requires rigorous parity testing |
| ## Dispatch Service | ## DISPATCH, DISPATCH_DA, DISPATCH_FUNCTIONS, DISPATCHASSIGN, DISPATCH_DATA_OBJ, DISPATCH3, PHYSICALDISPATCH | ## XL-tier (16,833 effective LOC); vendor selection, routing, email confirmation via UTL_SMTP (→ Notification Service); critical coupling to Vendor and Contract services |
| ## Service Order Service | ## Subset of SERVICE, SERVICEITEM, SERVICEITEM_DA, SERVICE_WM (P1 subset) | ## Stub-level P1 delivery; full implementation in P3. Absorbs Service Request (D7) |
| ## Work Order & Fulfillment | ## Subset of WORKORDER, WORKORDER_DA, FULFILLMENT_FUNCTIONS, PRODUCT_AVAILABILITY, DISTRIBUTOR_FUNCTIONS | ## Stub-level P1 delivery; full implementation in P2. Critical coupling to Contract and Customer services |
| ## Invoicing Service | ## CREATE_INVOICES, CREATE_BILLING_INVOICES, STAGEDINVOICEBATCH, STAGEDINVOICEBATCH_DA | ## Invoice creation, batch processing, staged-invoice validation; coupling to Finance Integration for JDE staging |
| ## Payment Service | ## PAYMENT_LOAD, PAYMENT_PROCESS, OVERDUE_PAYMENT, PROC_LOCKBOX_BATCHES, PKG_CREDIT_CARD_STAGING, PKG_CP_STAGING | ## Payment batch ingestion, lockbox processing, credit-card staging; coupling to Card Security for decryption |
| ## Vendor Service | ## Subset of VENDOR, VENDOR_DA, VENDOR_LIST, VENDORSELECTION | ## Vendor master data, selection algorithms; coupling to Dispatch |
| ## Vendor Invoice & Writeoff | ## VENDORINVOICE, VENDORINVOICE_DA, PKG_AP_STAGING, PKG_AP_REVERSE_STAGING, PKG_VENDORS_STAGING, PKG_AUTO_WRITEOFF_PROCESS, SERVICEPAYABLE, SERVICEPAYABLE_DA, PPUB_INVOICE_DIST, PROC_CREDIT_MEMO_APPLY (additional_code) | ## AP staging, invoice distribution, credit-memo batch; critical coupling to Finance Integration and Invoicing |
| ## Commission & Territory | ## PKG_SALES_COMMISSION_ENGINE, SALES_TERRITORY_RULES, SALES_FUNCTIONS (partial) | ## Commission engine, territory-rule evaluation; financial logic requiring strict parity |
| ## Finance Integration | ## PKG_JDE_SYNC (partial), GET_GL_CODE_PKG, CREATE_AP_JDE_FILE, CREATE_GL_JDE_FILE, CREATE_VENDOR_JDE_FILE, PROC_MISC_CASH_STAGING, PROC_OAP_PAYMENTS_STAGING (additional_code) | ## GL code determination, JDE flat-file generation/staging, data synchronization; absorbs General Ledger and MIM Integration (D7) |
| ## Card Security (PCI) | ## PKG_ACCT_DECRYPTION_FUNCTIONS (partial), PKG_ACCT_ENCRYPTION_FUNCTIONS | ## PCI-scoped: card decryption/encryption, VALIDATECREDITCARD function; AWS KMS integration |
| ## Reporting Service | ## PKG_ACCT_REPORTS, REPORT_SER147_FUNCTIONS, REPORT_UTILITY (partial) | ## Account reports, exception reporting; read-heavy query patterns |

## 2.7 Verify

## Functional testing. Execute test suites per service: unit, integration, contract tests.

## Performance parity testing. Compare API response times against legacy PL/SQL execution times; target: no degradation beyond 10% p95 latency.

## Behavioral parity testing. For each service, execute the parity test suite (identical inputs → PL/SQL vs .NET → compare outputs). Minimum pass rate: 95% scenario coverage at 100% match.

## UAT coordination. Frontdoor-led user acceptance testing; 66degrees provides environment support, defect intake, and remediation.

## Defect remediation. Fix cycle within Verify; severity-1/2 defects block phase close-out.

## 2.8 Operate

## SRE handover. Per-service runbooks, CloudWatch dashboards, alerting rules, escalation procedures.

## Knowledge transfer. Structured KT sessions to Frontdoor's SRE and development teams covering: service architecture, deployment procedures, mesh routing management, rollback procedures.

## Documentation finalization. Per-service: API documentation (OpenAPI), architecture decision records (ADRs), sequence diagrams, deployment guide.

## Phase close-out. Retrospective, lessons-learned capture, next-phase planning inputs.

## 3. Phase 2 — Translate & Decommission Next 45 PL/SQL Objects

## Phase 2 starts mid-Phase 1. The team carries over from Phase 1 — no Prepare stage. 17 services touched (8 extensions of Phase 1 services + 3 net-new services + 6 additional extensions).

## New services introduced: Renewal · Campaign & Lead · Notification. Services extended: Customer · Pricing · Dispatch · Service Order · Work Order & Fulfillment · Invoicing · Payment · Vendor · Vendor Invoice · Commission & Territory · Finance Integration · Reporting · Sales Transaction (started) · Web Portal & User (started).

## 3.1 Define

## Extension delta analysis (8 services). For services already partially delivered in Phase 1, scope the additional PL/SQL packages being added — identifying only the incremental procedures, cross-package calls, and Oracle-proprietary constructs not previously addressed.

## Net-new service scoping (3 services). Full specification mining for Renewal Service (RENEWAL_BATCH_LIB, RENEWAL_BATCH, RENEWALS, PKG_EVERGREEN_RENEWAL, CONTRACT_RENEWAL_FUNCTIONS, LMS_RENEWALS_LOAD), Campaign & Lead Service (CAMPAIGN_LIB, DIALER_LEAD_MANAGEMENT), and Notification Service (COMMON_FUNC_EMAIL, COMMON_FUNC_EMAIL_INTERIM).

## External dependency. STAR_CLOUD has no implementation in package or additional_code exports; File & S3 Storage adapter is built from call sites in Phase 0.

## 3.2 Design

## API design and OpenAPI specs for new and extended services using AI-generated drafts with human review. Extensions require delta design only — new endpoints and modified DTOs, not full-service redesign.

## Sequence diagrams for new services (Renewal, Campaign & Lead, Notification).

## K8s manifest patterns reuse Phase 1 templates with per-service Kustomize overrides.

## 3.3 Plan

## Sprint plan for Build stage across 17 services.

## Release sequence respecting dependency order: Renewal depends on Contract (P1); Campaign depends on Invoicing (P1) and Customer (P1).

## 3.4 Value Checkpoint

## Sponsor sign-off on Phase 2 scope, updated risk register, Build plan.

## 3.5 Build

## Phase 2 translation follows the same per-service pipeline as Phase 1, with reduced architect and associate staffing reflecting pattern maturity.

## Phase 2 service-specific scope:

| ## Service | ## PL/SQL packages translated | ## Key technical concerns |
| --- | --- | --- |
| ## Renewal Service (new) | ## RENEWAL_BATCH_LIB, RENEWAL_BATCH, RENEWALS, PKG_EVERGREEN_RENEWAL, CONTRACT_RENEWAL_FUNCTIONS, LMS_RENEWALS_LOAD | ## Evergreen auto-renewal, LMS data load, renewal batch processing; depends on Contract, Pricing, Work Order |
| ## Campaign & Lead Service (new) | ## CAMPAIGN_LIB, DIALER_LEAD_MANAGEMENT | ## Lead creation/close for dialer campaigns; integrates with prod.star_cloud for file exchange (→ File & S3 Storage lib) |
| ## Notification Service (new) | ## COMMON_FUNC_EMAIL (partial) | ## Replaces UTL_SMTP-based email delivery with a REST-callable notification service; consumed by Dispatch, Service Order, Campaign |
| ## Work Order & Fulfillment (extend) | ## WORKORDER, WORKORDER_DA, FULFILLMENT_FUNCTIONS, CUSTOM_FULFILLMENT_FUNCTIONS, PRODUCT_AVAILABILITY, DISTRIBUTOR_FUNCTIONS (bulk) | ## XL-tier primary delivery phase; product availability, distributor functions, custom fulfillment, work-order lifecycle |
| ## Dispatch Service (extend) | ## Additional DISPATCH/DISPATCH3/DISPATCH_DATA_OBJ procedures | ## Extended routing logic, data-object management |
| ## Customer Service (extend) | ## CUSTOMER_DA, CUSTOMER_FUNCTIONS (remaining), SEARCH_FUNCTIONS (partial) | ## Customer data access, extended search |
| ## Vendor Service (extend) | ## VENDOR (bulk), VENDOR_DA (bulk), VENDORSELECTION (bulk) | ## Vendor master management, selection algorithms |
| ## Commission & Territory (extend) | ## SALES_TERRITORY_RULES (remaining), SALES_FUNCTIONS (remaining) | ## Territory-rule completion |
| ## Service Order (extend) | ## SERVICE (partial), SERVICEITEM, SERVICEITEM_DA, CONFRM_PKG | ## Service-order confirmation, service-item management |
| ## Invoicing (extend) | ## PRINT_DIRECT_INVOICE_MAILERS, STAGEDINVOICEBATCH (remaining) | ## Invoice mailers, staged-batch completion |
| ## Web Portal & User (started) | ## AHS_WEB_FUNCTIONS, AHSUSERFUNCTIONS (partial) | ## Web session resolution, user functions; replaces Oracle Web Toolkit (HTP/HTF) HTML generation with REST responses |
| ## Sales Transaction (started) | ## SALES_TRANSACTION_ENGINE (partial) | ## Sales contract save, product-version validation; start of P3-dominant service |
| ## Pricing & Revenue (extend) | ## PRICE_CONTRACT_WARRANTY (remaining) | ## Warranty pricing completion |
| ## Payment (extend) | ## Remaining PAYMENT_FUNCTIONS procedures | ## Payment function extensions |
| ## Vendor Invoice (extend) | ## Remaining AP-staging procedures | ## AP staging completion |
| ## Finance Integration (extend) | ## PKG_JDE_SYNC delta | ## JDE sync extensions |
| ## Reporting (extend) | ## REPORT_UTILITY (partial) | ## Report utility extensions |

## Istio routing (Phase 2). Per-service VirtualService/DestinationRule configuration using templates proven in Phase 1. Traffic-split progression for each newly delivered or extended service on the existing mesh.

## 3.6 Verify

## Functional, integration, contract, performance-parity, and behavioral-parity testing per Phase 1 model. Frontdoor-led UAT.

## 3.7 Operate

## SRE handover, KT, documentation finalization, phase close-out.

## 4. Phase 3 — Translate & Decommission Final 39 PL/SQL Objects

## Phase 3 starts mid-Phase 2. 17 services touched, predominantly extensions. Only one net-new service (Cancellation).

## New service introduced: Cancellation. Services extended: All remaining services receive final PL/SQL packages.

## 4.1 Define

## Extension delta analysis for 16 services; full scoping for Cancellation Service (CONTRACT_CANCEL_FUNCTIONS, CASHINLIEU).

## Supplemental source. Ten Phase 3 standalone objects are in src/additional_code/ (CLOB_TO_FILE, COST_CENTER2DEPARTMENT, DEQUEUE_MESSAGE, ENQUEUE_MESSAGE, FLAG_CS1, MASK_CC_DATA, PPUB_REVERSE_PAYMENT, PPUB_SERVICEFEE_WRITEOFF, VALIDATECREDITCARD, PROC_INCREMENT_USAGE_COUNT). PROC_INCREMENT_USAGE_COUNT is a discontinued stub. COMMON_FUNC_EMAIL_ROB3 remains absent (confirm with Frontdoor). DEQUEUE_MESSAGE / ENQUEUE_MESSAGE are out of modernization build scope (Frontdoor-owned AQ on prod.myqueue). Wrappers and VALIDATECREDITCARD reconcile with scoped packages (P_LIBRARIES, PKG_AUTO_WRITEOFF_PROCESS, PKG_ACCT_DECRYPTION_FUNCTIONS).

## 4.2 Design

## API design for Cancellation Service (refund calculation, cancellation-request submission, cash-in-lieu offer management).

## Delta design for 16 extension services.

## Card Security extension review: PCI re-validation for VALIDATECREDITCARD function and MASK_CC_DATA equivalent behavior.

## 4.3 Plan

## Sprint plan for Build stage.

## Final release sequence: Cancellation depends on Contract (P1) and Service Order (P2); Service Order receives bulk delivery.

## 4.4 Value Checkpoint

## Final phase sponsor sign-off.

## 4.5 Build

## Phase 3 service-specific scope:

| ## Service | ## PL/SQL packages translated | ## Key technical concerns |
| --- | --- | --- |
| ## Cancellation Service (new) | ## CONTRACT_CANCEL_FUNCTIONS, CASHINLIEU | ## Refund calculation (state-specific, channel-specific, timing-dependent rules), cancellation-request workflow, cash-in-lieu offer/accept; critical coupling to Contract |
| ## Service Order (primary) | ## SERVICE (bulk), SERVICEITEM/SERVICEITEM_DA (remaining), SERVICE_WM, CONFRM_PKG (remaining) | ## P3-dominant service; recall detection, service-item lifecycle, work-order symptom management; absorbs Service Request |
| ## Vendor Service (extend) | ## VENDOR/VENDOR_DA/VENDORSELECTION (remaining), VENDOR_LIST | ## Vendor-list management, selection algorithm completion |
| ## Sales Transaction (extend) | ## SALES_TRANSACTION_ENGINE (remaining) | ## Contract save for all channels (B2B, RE, DTC), product-version validation completion |
| ## Renewal (extend) | ## LMS_RENEWALS_LOAD (remaining), RENEWAL_BATCH (remaining) | ## LMS load completion, batch renewal finalization |
| ## Work Order & Fulfillment (extend) | ## Remaining PRODUCT_AVAILABILITY, DISTRIBUTOR_FUNCTIONS procedures | ## Product availability and distributor-function completion |
| ## Customer (extend) | ## SEARCH_FUNCTIONS (remaining), CUSTOMER_FUNCTIONS (remaining) | ## Enterprise search completion |
| ## Dispatch (extend) | ## DISPATCH2, remaining dispatch procedures | ## Secondary dispatch logic |
| ## Web Portal & User (extend) | ## AHS_WEB_FUNCTIONS (remaining), AHSUSERFUNCTIONS (remaining), WEB_INTERNET_FUNCTIONS | ## Web function completion; internet address validation |
| ## Finance Integration (extend) | ## PKG_MIM2STAR_INTEGRATION, PKG_GL_FUNCTIONS, PKG_SERVICE_PAYABLES | ## MIM-to-STAR integration, GL functions, service payables; absorbs GL and MIM (D7). prod.cost_center2department handled via adapter. |
| ## Reporting (extend) | ## REPORT_UTILITY (remaining) | ## Report utility completion |
| ## Card Security (extend) | ## PKG_ACCT_DECRYPTION_FUNCTIONS (remaining), VALIDATECREDITCARD, MASK_CC_DATA (additional_code) | ## Credit-card validation and masking; reconcile standalone vs package validatecreditcard; PCI re-validation |
| ## Invoicing (extend) | ## Remaining invoicing procedures | ## Final invoice processing logic |
| ## Notification (extend) | ## COMMON_FUNC_EMAIL (remaining) | ## Email template completion |
| ## Payment (extend) | ## PAYMENT_FUNCTIONS (remaining), TPV_INVOICE | ## TPV invoice handling, payment function completion |
| ## Vendor Invoice (extend) | ## Remaining AP procedures | ## Final AP-staging logic |

## Istio routing (Phase 3). Per-service routing configuration using proven templates. By Phase 3 close, all 18 services have VirtualService/DestinationRule configurations enabling progressive cutover on the existing mesh.

## 4.6 Verify

## Same model as Phase 2. Full behavioral-parity testing for all 18 services.

## 4.7 Operate

## Final SRE handover. Complete handover packet for all 18 services and 6 shared libraries.

## Program-level knowledge transfer. Comprehensive KT covering: Istio strangler-routing operations for this program (traffic splitting, per-service VirtualService management, project AuthorizationPolicy updates), CI/CD pipeline ownership, monitoring/alerting, rollback procedures. Cluster-wide mesh operations (control-plane upgrades, sidecar lifecycle, mTLS rotation) remain Frontdoor-owned.

## Final documentation. Program-level architecture handbook, per-service API documentation, Istio routing playbook for project VirtualServices.

## Program close-out. Final retrospective, lessons learned, formal program completion.

### Follow-up Questions from the Team:

Team - feel free to add your follow-up questions here.

- Question #1

- Question #2

- …

## Project Scope

The scope of services 66degrees will deliver during this engagement will be divided into the following categories: See Appendix B for Architecture Diagram of migration approach.

- Phase 1: Core Transactional Domains

● Functional Scope: Modernization of fifty-two (52) validated PL/SQL objects spanning Sales Origination & Pricing, Service Dispatch, and Vendor Management domains (listed in Appendix 1).

● Target Architecture: Provisioning of corresponding .NET microservices deployed via containerization.

● Rollout Framework: Execution of a progressive Strangler Fig deployment pattern. Author project-scoped Istio service mesh configurations—specifically VirtualService,

DestinationRule, and AuthorizationPolicy manifests—within Frontdoor’s existing AWS Elastic Kubernetes Service (EKS) infrastructure to enable incremental, weighted traffic splitting and rapid rollback execution.

- Phase 2: Financial & Invoicing Operational Domains

- Functional Scope: Modernization of forty-one (41) validated PL/SQL objects spanning Payment Processing, Invoicing, and Commission Calculation domains (listed in Appendix 1).

- Target Architecture: Extension of the .NET service mesh, ensuring transactional security parameters are preserved.

- Phase 3: ERP Integration & Ledger Domains

- Functional Scope: Modernization of twenty-nine (29) validated PL/SQL objects governing Financial Reconciliation with the JDE (ERP) system

- Target Architecture: Finalization of the 18 target microservices and completion of the logical decoupling from the legacy Oracle monolith execution paths.

## Deliverables Ownership

Use the section below to align upon Deliverables ownership.

| Deliverable | Owner (i.e. who’s chiefly Accountable for the Deliverable?) | Support(ers) (i.e. who provides key inputs and/or internally reviews the Deliverable?) |
| --- | --- | --- |
| Project Kickoff Materials | Delivery Manager | Principals |
| Status Report & Financial Updates | Delivery Manager | Scrum Masters |
| 18 Domain-Aligned .NET REST Microservices | Project Dev + QA Team | Principals & Architects |
| 6 Shared NuGet Libraries | Project Dev + QA Team | Individual Scrum Teams |
| Reference Architecture Document | Pod Architects | TBD |
| CI/CD Pipelines | Project Team | TBD |
| Program Architecture Documentation | Pod Architects | TBD |
| Structured Knowledge Transfer (KT): |  | All Team Members |

## Risk Management

Use the section below to list any Risks that the project team identifies at the outset of the project and the next action(s) to mitigate the Risks. Logs risks on your project record as applicable.

| Risk, Issue, Question | Type | How could this Risk impact the project? | Step(s) to Mitigate |
| --- | --- | --- | --- |
| Dead-code factor proves inaccurate | Risk | If actual live code exceeds 50%, build scope is undersized; if below 50%, the program has excess capacity. | Phase 0 golden-example exercise provides a first calibration. Phase 1 Define call-graph analysis provides a second. Formal re-baseline gate at Phase 1 Value Checkpoint. |
| Strangler fig requires legacy PL/SQL exposed as REST | Risk | If Frontdoor cannot expose legacy endpoints via ORDS or equivalent, traffic splitting is blocked. | Confirm ORDS capability during Phase 0 Design. If legacy REST exposure is delayed, services deploy behind mesh but use big-bang cutover per service (mesh still provides mTLS and observability). Rollback procedure validated in Phase 0 POC. |
| Requirements drift without embedded BA. | Risk | App Dev Architects and Senior Engineers own requirements extraction; misinterpretation risk exists without a dedicated BA. | AI-extracted PL/SQL specifications provide a machine-auditable requirements baseline. Weekly Frontdoor-BA validation gates during Define. |
| No hypercare means production defects land on Frontdoor. | Risk | Post-go-live defects discovered after the Operate stage are Frontdoor's responsibility. | Stabilization within Operate (deploy → monitor → close-out). Defect-severity gates inside Verify. Frontdoor SRE knowledge transfer is an explicit Operate deliverable. |
| AI productivity assumptions under-realized. | Risk | The AI uplift may not materialize for complex PL/SQL idioms (e.g., deeply nested cursor loops, Oracle-specific date arithmetic, NLS_-dependent string operations). | Dead-code factor (50%) provides implicit buffer. Phase 0 golden-example exercise calibrates actual AI rate and dead-code ratio before Phase 1 commitment. Re-baseline at Value Checkpoint if variance is significant. |
| UAT delays due to Frontdoor BA/SME/user availability. | Risk | Schedule dealy: Frontdoor's business-analyst, SME, and end-user availability is not controlled by 66degrees. | DM books UAT slots at Plan stage. UAT failures attributed to Frontdoor-side capacity are change-control items. |
| PCI scope expansion | Risk | Card Security service handling may force enclaved infrastructure requirements beyond what is currently planned. | Phase 0 PCI scope analysis. AWS KMS-backed Crypto Primitives library isolates key material. If PCI scope expands, additional infrastructure is a change-control item. |
| AI translation introduces semantic drift in financial logic. | Risk | Commission calculation, write-off processing, credit-memo application, and deferred-revenue computation involve complex business rules where subtle behavioral differences can cause material financial impact. | Mandatory pair-review by senior engineer for all financial logic. Dedicated parity-test suites compare PL/SQL output vs .NET output for ≥90% of known scenarios. Financial services flagged for extended Verify. |

Note to Project Manager: If a pre-flight risk assessment has been completed for the project, include any risks identified here.

## Action Items

| Action Item | Owner | Status |
| --- | --- | --- |
|  |  | Completed |
|  |  | In Progress |
|  |  | Completed |
|  |  | In Progress |
|  |  | In Progress |
|  |  | In Progress |
|  |  | In Progress |
|  |  | In Progress |